## Scorecard
The Bid Margin Scorecard
Project name:
Bid amount:
Q1 — Customer-mix risk | Have you completed a project for this customer before?
Your answer:
Q2 — Geography risk | Have you self-performed work in this state in the last 24 months?
Your answer:
Q3 — Prevailing wage / labor compliance | What's the labor classification?
Your answer:
Q4 — Materials lead-time risk | For your top 3 long-lead items, are vendor lead-times within historical baseline?
Your answer:
Q5 — Crew availability | Will you need new crew (internal or sub) to staff this project on the proposed schedule?
Your answer:
Q6 — Concurrent project load | How many active projects will overlap with this one in months 1-6?
Your answer:
Q7 — Change-order pattern | For projects with this customer or in this market, what's the typical CO frequency?
Your answer:
Q8 — Margin-erosion baseline | For your last 3 projects of similar type/size, what's the average margin variance from bid?
Your answer:
Q9 — IRA/PTC/ITC qualification | If this project qualifies for tax credits, are you fully versed in credit-stacking and domestic-content requirements?
Your answer:
Q10 — Subcontractor depth | For the major subcontracted scopes, do you have at least 2 qualified subs willing to bid?
Your answer:
Q11 — Schedule risk | Is the customer's required completion date within your normal cadence, or are they pushing?
Your answer:
Q12 — Bonding capacity | Will this project consume more than 25% of your remaining bonding capacity?
Your answer:
Total score:
Recommendation:

## Calculation (hidden)
Q1 answer | points | Q2 answer | points | Q3 answer | points | Q4 answer | points | Q5 answer | points | Q6 answer | points | Q7 answer | points | Q8 answer | points | Q9 answer | points | Q10 answer | points | Q11 answer | points | Q12 answer | points
Yes, multiple — they pay on time, COs are reasonable | 10 | Yes, multiple projects | 5 | Open shop, no PW exposure | 5 | Yes, all 3 | 10 | No, existing crews can absorb | 5 | 1-3 (no resource collision) | 5 | Low (<5% of contract value) | 5 | +0% to +5% (you bid accurately) | 5 | Yes, our team has done it before | 5 | Yes, all major scopes | 5 | Comfortable timeline | 5 | No, comfortable headroom | 5
Yes, once — pay was OK, no major drama | 5 | Yes, one project | 0 | Federal Davis-Bacon, you've handled it before | 0 | 2 of 3 | 0 | Some — 1-2 new positions or a known sub | 0 | 4-7 (manageable, requires coordination) | 0 | Medium (5-15%) | 0 | -1% to -3% (typical drift) | 0 | Partial — we'll need outside counsel | 0 | Most, but 1 scope is single-source | -2 | Tight but doable | 0 | Yes, but cycle of completion is short | 0
No, but they're a known industry name | 0 | No, but you have crew willing to travel | -5 | State PW (Cal-OSHA, NY, IL, etc.), you've handled it before | -2 | 1 of 3 | -10 | Significant — multiple new hires or unknown sub | -10 | 8-12 (real strain) | -10 | High (15-30%) | -5 | -4% to -8% (real erosion) | -10 | No — we're learning on this project | -10 | Multiple single-source scopes | -10 | Tight, requires overtime baseline | -10 | Yes, and it ties up capacity for 18+ months | -10
No, and they're new to large-scale work | -10 | No, and you'd need to hire local | -10 | State PW, you have NOT handled it before | -10 | None | -20 | Yes, you'd need to grow headcount 20%+ | -15 | 13+ (you're saturating) | -20 | Customer is known for unbilled change demands | -15 | -9%+ (this is a pattern, not noise) | -15 | N/A — project doesn't qualify | 0 | You have 1 sub for everything and they're booked | -20 | Unrealistic — you'd need to bake LD risk in | -15